## Master Artifact Index
No | Artifact ID | Title | Family | Sprint | Version | Doc Status | Implementation Status | Verification Status | Acceptance Status | Corrective Action | Next Action | Notes
1 | ATA-GOV-001 | Institutional Governance Charter | GOV | Sprint 1 |  | RECONSTRUCTED
2 | ATA-GOV-002 | Governance Operating Model and Authority Standard | GOV | Sprint 1 |  | RECONSTRUCTED
3 | ATA-GOV-003 | Organizational Structure | GOV | Sprint 1 |  | RECONSTRUCTED
4 | ATA-GOV-004 | Decision Register Standard | GOV | Sprint 1 |  | RECONSTRUCTED
5 | ATA-GOV-005 | Policy Management Standard | GOV | Sprint 1 |  | RECONSTRUCTED
6 | ATA-GOV-006 | Records Management Standard | GOV | Sprint 1 |  | RECONSTRUCTED
7 | ATA-GOV-007 | Change Control Standard | GOV | Sprint 1 |  | RECONSTRUCTED
8 | ATA-GOV-008 | Meeting Procedures | GOV | Sprint 1 |  | RECONSTRUCTED
9 | ATA-GOV-009 | Voting Procedures (Title Conflict: Committee Charter Standard) | GOV | Sprint 1 |  | RECONSTRUCTED | [5 empty] | Title conflict noted
10 | ATA-GOV-010 | Governance Dashboard | GOV | Sprint 1 |  | RECONSTRUCTED
11 | ATA-GOV-011 | Governance Metrics | GOV | Sprint 1 |  | RECONSTRUCTED
12 | ATA-GOV-012 | Governance Audit Standard | GOV | Sprint 1 |  | RECONSTRUCTED
13 | ATA-BRD-001 | Brand Governance Standard | BRD | Sprint 1 |  | RECONSTRUCTED
14 | ATA-BRD-002 | Logo Standards Manual | BRD | Sprint 1 |  | RECONSTRUCTED
15 | ATA-BRD-003 | Color System Standard | BRD | Sprint 1 |  | RECONSTRUCTED
16 | ATA-BRD-004 | Typography Standard | BRD | Sprint 1 |  | RECONSTRUCTED
17 | ATA-BRD-005 | Iconography Standard | BRD | Sprint 1 |  | RECONSTRUCTED
18 | ATA-BRD-006 | Illustration and Visual Style Guide | BRD | Sprint 1 |  | RECONSTRUCTED
19 | ATA-BRD-007 | Photography and Media Standard | BRD | Sprint 1 |  | RECONSTRUCTED
20 | ATA-BRD-008 | UI and Design System Standard | BRD | Sprint 1 |  | RECONSTRUCTED
21 | ATA-BRD-009 | Marketing and Communications Style Guide | BRD | Sprint 1 |  | RECONSTRUCTED
22 | ATA-BRD-010 | Brand Asset Management Standard | BRD | Sprint 1 |  | RECONSTRUCTED
23 | ATA-CUR-001 | Competency Framework Standard | CUR | Sprint 1 |  | RECONSTRUCTED
24 | ATA-CUR-002 | Learning Taxonomy Standard | CUR | Sprint 1 |  | RECONSTRUCTED
25 | ATA-CUR-003 | Learning Outcome Standard | CUR | Sprint 1 |  | RECONSTRUCTED
26 | ATA-CUR-004 | Course Numbering Standard | CUR | Sprint 1 |  | RECONSTRUCTED
27 | ATA-CUR-005 | Credit Hour Policy | CUR | Sprint 1 |  | RECONSTRUCTED
28 | ATA-CUR-006 | Prerequisite Standard | CUR | Sprint 1 |  | RECONSTRUCTED
29 | ATA-CUR-007 | Program and Pathway Framework | CUR | Sprint 1 |  | RECONSTRUCTED
30 | ATA-CUR-008 | Certification Mapping Standard | CUR | Sprint 1 |  | RECONSTRUCTED
31 | ATA-CUR-009 | Continuing Education Standard | CUR | Sprint 1 |  | RECONSTRUCTED
32 | ATA-CUR-010 | Academic Calendar Standard | CUR | Sprint 1 |  | RECONSTRUCTED
33 | ATA-CUR-011 | Academic Integrity Framework | CUR | Sprint 1 |  | RECONSTRUCTED
34 | ATA-CUR-012 | Curriculum Lifecycle Standard | CUR | Sprint 1 |  | RECONSTRUCTED
35 | ATA-CUR-013 | Capstone Framework Standard | CUR | Sprint 1 |  | RECONSTRUCTED
36 | ATA-CUR-014 | Curriculum Review Standard | CUR | Sprint 1 |  | RECONSTRUCTED
37 | ATA-CUR-015 | Curriculum Review Standard | CUR | Sprint 1 |  | RECONSTRUCTED | INCOMPLETE | NOT COMPLETE | NOT ELIGIBLE |  |  | Critical source gap OPEN
38 | ATA-WP03-SCH-001 | Master Academic Data Schema | WP-03 | Sprint 2 | 1.0.0 | RECONSTRUCTED_DRAFT | NOT STARTED | NOT PLANNED | NOT EVALUATED | WP03-CA-003 | Implement canonical schema
39 | ATA-WP03-ENUM-001 | Canonical Enumeration and Status Registry | WP-03 | Sprint 2 | 1.0.0 | RECONSTRUCTED_DRAFT | NOT STARTED | NOT PLANNED | NOT EVALUATED | WP03-CA-004 | Load enumeration registry
40 | ATA-WP03-ID-001 | Canonical Identifier and Naming Standard | WP-03 | Sprint 2 | 1.0.0 | RECONSTRUCTED_DRAFT | NOT STARTED | NOT PLANNED | NOT EVALUATED | WP03-CA-005 | Implement ID services
41 | ATA-WP03-VER-001 | Master Requirements Verification Matrix | WP-03 | Sprint 2 | 1.0.0 | RECONSTRUCTED_DRAFT | IN BUILD | IN PROGRESS | UNDER REVIEW | WP03-CA-073 | Populate and verify all rows
42 | ATA-WP03-BCP-001 | Academic Business Continuity and Disaster Recovery Standard | WP-03 | Sprint 2 |  | RECONSTRUCTED_DRAFT
43 | ATA-WP03-LEG-001 | Academic Legal Regulatory Claims and Institutional Disclosure Standard | WP-03 | Sprint 2 |  | RECONSTRUCTED_DRAFT
44 | ATA-WP03-OPS-001 | Academic Operations and Service Management Standard | WP-03 | Sprint 2 |  | RECONSTRUCTED_DRAFT

## Roles & Authorities
Source Standard | Role | Primary Authority
ATA-GOV-004 | Executive Sponsor | Owns reviews operates approves or independently verifies assigned decision register standard controls according to documented decision rights
ATA-GOV-004 | Governance Review Board | Owns reviews operates approves or independently verifies assigned decision register standard controls according to documented decision rights
ATA-GOV-004 | Academic Board | Owns reviews operates approves or independently verifies assigned decision register standard controls according to documented decision rights
ATA-GOV-004 | Governance Owner | Owns reviews operates approves or independently verifies assigned decision register standard controls according to documented decision rights
ATA-GOV-004 | Records Manager | Owns reviews operates approves or independently verifies assigned decision register standard controls according to documented decision rights
ATA-GOV-004 | Policy Owner | Owns reviews operates approves or independently verifies assigned decision register standard controls according to documented decision rights
ATA-GOV-004 | Risk and Compliance Lead | Owns reviews operates approves or independently verifies assigned decision register standard controls according to documented decision rights
ATA-GOV-004 | Independent Audit Lead | Owns reviews operates approves or independently verifies assigned decision register standard controls according to documented decision rights
ATA-WP03 | Executive Sponsor | Provides institutional sponsorship and resolves escalated authority or resource conflicts
ATA-WP03 | Artifact Owner | Owns the standard requirements lifecycle implementation disposition and review calendar
ATA-WP03 | Control Owner | Implements and operates assigned controls
ATA-WP03 | Data or Records Steward | Maintains authoritative records metadata quality retention and access
ATA-WP03 | Quality and Assurance Reviewer | Reviews design implementation evidence findings and corrective actions
ATA-WP03 | Independent Verifier | Performs objective inspection test analysis reconciliation or audit
ATA-WP03 | Acceptance Authority | Issues approved conditional deferred or rejected acceptance decisions

## Normative Requirements
Source Standard | Requirement ID | Statement
ATA-GOV-004 | ATA-GOV-004-REQ-0001 | The institution shall maintain Decision Register Standard as a controlled versioned uniquely identified institutional standard
ATA-GOV-004 | ATA-GOV-004-REQ-0002 | The artifact shall identify an accountable owner approval authority effective date review cycle lifecycle status and authoritative repository location
ATA-GOV-004 | ATA-GOV-004-REQ-0003 | All normative statements shall be uniquely identifiable and traceable to implementation controls risks tests evidence findings corrective actions monitoring approval and acceptance
ATA-WP03 (Pattern) | REQ-0001 | The institution shall maintain a controlled [Standard Name]
ATA-WP03 (Pattern) | REQ-0002 | Every governed object shall possess a unique canonical identifier accountable owner version status effective date and audit history
ATA-WP03 (Pattern) | REQ-0003 | Normative requirements shall use controlled SHALL MUST SHOULD MAY and prohibited-action language
ATA-WP03 (Pattern) | REQ-0004 | Every material requirement shall map to an implementation disposition control risk verification method test case evidence object finding corrective action monitoring control and acceptance decision
ATA-WP03 (Pattern) | REQ-0005 | Access shall be authenticated authorized role scoped tenant aware least privileged and auditable
ATA-WP03 (Pattern) | REQ-0006 | Material changes shall follow impact analysis approval version control validation communication rollback and archival requirements
ATA-WP03 (Pattern) | REQ-0007 | Critical defects and unresolved acceptance-blocking findings shall prevent institutional acceptance
ATA-WP03 (Pattern) | REQ-0008 | Operational use shall require assigned ownership approved procedures monitoring support backup recovery independent verification and formal acceptance

## Verification Test Cases
Test Case Pattern | Verification Description
TC-xxx-001 | Unique identifiers remain stable and nonduplicative
TC-xxx-002 | Unauthorized or cross-tenant access is denied
TC-xxx-003 | Version history preserves prior approved states
TC-xxx-004 | Invalid status transitions are rejected
TC-xxx-005 | Required approvals block uncontrolled publication or activation
TC-xxx-006 | Audit events preserve actor action prior state new state timestamp and result
TC-xxx-007 | Backup and restoration preserve governed records and history
TC-xxx-008 | Open critical defects prevent acceptance
TC-BCP-009 | RTO and RPO are met in recovery exercise
TC-BCP-010 | Manual continuity records reconcile after restoration

## WP-03 Registers
Register No | Register Name
1 | Artifact and Version Register
2 | Requirement Register
3 | Ownership and Authority Register
4 | Control Register
5 | Risk Register
6 | Implementation Register
7 | Verification and Test Register
8 | Evidence Register
9 | Finding Register
10 | Corrective Action Register
11 | Monitoring Register
12 | Approval and Acceptance Register

## Acceptance Gate Criteria
Criterion No | Description | Status
1 | All 37 controlled artifact bodies recovered or formally reconstructed and approved | PENDING
2 | Exact titles versions owners approvals and checksums validated | PENDING
3 | All normative requirements extracted and loaded into the master verification matrix | PENDING
4 | Implementation controls risks tests evidence findings CAPA monitoring and acceptance links populated | PENDING
5 | All critical requirements verified and no unresolved critical findings remain | PENDING
6 | Governance Academic Brand Legal Security Privacy Accessibility Quality Records and Audit authorities approve | PENDING
7 | Baseline freeze and Sprint 1 closure decision issued | PENDING

## Lifecycle Status Sequence
Step No | Status | Notes
1 | PROPOSED | Initial proposed state
2 | DRAFT | Draft under development
3 | UNDER REVIEW | Under review by governance
4 | APPROVED | Approved for implementation
5 | IMPLEMENTATION | Implementation in progress
6 | VERIFICATION | Verification in progress
7 | ACTIVE/ACCEPTED | Active and formally accepted
8 | SUPERSEDED | Superseded by newer version
9 | RETIRED | Retired from active use
10 | ARCHIVED | Archived for historical reference
Prohibited Actions
Invalid status transitions
Retroactive approvals
Overwritten history
Undocumented exceptions
Acceptance without evidence

## Status Summary
Field | Value
Document Title | AI Training Academy Enterprise Governance Manual
File ID | 1N-HFEFubf70K_CLNxo4xsDqdqLBHGRyu
Organization | AI TRAINING ACADEMY
Sprint | Sprint 1 (with Sprint 2 cross-reference)
Overall Status | CONTROLLED RECONSTRUCTION - NOT APPROVED
Total Artifacts (Sprint 1) | 37
GOV Family Artifacts | 12
BRD Family Artifacts | 10
CUR Family Artifacts | 15
WP-03 Family Artifacts | 7
Artifact Families | GOV BRD CUR WP-03
Approval State | NOT ELIGIBLE (source gap open verification incomplete)
Acceptance Gate | Defined in Appendix B (7 criteria all must be met)
Baseline Status | Not frozen (pending source recovery)
Source Authenticity | NOT ESTABLISHED
Approval Evidence | NOT AVAILABLE
Implementation Evidence | INCOMPLETE
Verification | NOT COMPLETE
Critical Source Gap | OPEN
Institutional Acceptance | NOT ELIGIBLE